## Estimate VS Actual Effort
Row Labels | Sum of Estimated Effort | Sum of Actual Effort
Sprint 1 | 13 | 14
Sprint 2 | 12 | 16
Sprint 3 | 7 | 7
Sprint 4 | 11 | 11
Grand Total | 43 | 48

## Project wise Estimate VS Actual
Row Labels | Sum of Estimated Effort | Sum of Actual Effort
Project 1 | 26 | 29
Project 2 | 6 | 8
Project 3 | 11 | 11
Grand Total | 43 | 48

## Defect Sheet
DefectID | Description | Issue Date | Task | Status | Fixed Date
1 | Defect 1 | 2021-03-22 | Task 6 | Closed | 2021-03-22
2 | Defect 2 | 2021-03-22 | Task 7 | Closed | 2021-03-22
3 | Defect 3 | 2021-03-23 | Task 11 | Closed | 2021-03-23
4 | Defect 4 | 2021-03-23 | Task 12 | Closed | 2021-03-23
5 | Defect 5 | 2021-03-25 | Task 20 | Fixed | 2021-03-25
6 | Defect 6 | 2021-03-25 | Task 21 | Open

## Task Status Summary per Sprint
Count of Task | Column Labels
Row Labels | Done | In Progress
Sprint 1 | 5 | 2
Sprint 2 | 4 | 3
Sprint 3 | 5
Sprint 4 | 5 | 2

## Task Status Summary per project
Count of Task | Column Labels
Row Labels | Done | In Progress
Project 1 | 13 | 2
Project 2 | 1 | 3
Project 3 | 5 | 2

## Resource wise effort distributi
Row Labels | Sum of Estimated Effort | Sum of Actual Effort
Resource 1 | 21 | 23
Resource 2 | 22 | 25

## DASHBOARD
SPRINT DATA DASHBOARDING
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Sprint Tasks
Assignment Come up with different reports using the two tables for effective project management, quality, etc
Sl # | Sprint | Project | Task | Estimated Effort | Actual Effort | Resource | Task Status | Activity | Start Date | End Date
1 | Sprint 1 | Project 1 | Task 1 | 2 | 2 | Resource 1 | Done | Development | 2021-03-22 | 2021-03-22
2 | Sprint 1 | Project 1 | Task 2 | 3 | 3 | Resource 2 | Done | Development | 2021-03-22 | 2021-03-22
3 | Sprint 1 | Project 1 | Task 3 | 1 | 2 | Resource 1 | Done | Development | 2021-03-22 | 2021-03-22
4 | Sprint 1 | Project 1 | Task 4 | 2 | 3 | Resource 2 | Done | Development | 2021-03-22 | 2021-03-22
5 | Sprint 1 | Project 1 | Task 5 | 2 | 1 | Resource 1 | Done | Development | 2021-03-22 | 2021-03-22
6 | Sprint 1 | Project 1 | Task 6 | 2 | 2 | Resource 2 | In Progress | Testing | 2021-03-22 | 2021-03-22
7 | Sprint 1 | Project 1 | Task 7 | 1 | 1 | Resource 1 | In Progress | Testing | 2021-03-23 | 2021-03-23
8 | Sprint 2 | Project 1 | Task 6 | 2 | 4 | Resource 2 | Done | Testing | 2021-03-23 | 2021-03-23
9 | Sprint 2 | Project 1 | Task 7 | 1 | 2 | Resource 1 | Done | Testing | 2021-03-23 | 2021-03-23
10 | Sprint 2 | Project 1 | Task 8 | 3 | 2 | Resource 2 | Done | Development | 2021-03-23 | 2021-03-23
11 | Sprint 2 | Project 2 | Task 9 | 1 | 2 | Resource 2 | Done | Development | 2021-03-23 | 2021-03-23
12 | Sprint 2 | Project 2 | Task 10 | 2 | 2 | Resource 1 | In Progress | Development | 2021-03-23 | 2021-03-23
13 | Sprint 2 | Project 2 | Task 11 | 1 | 1 | Resource 1 | In Progress | Testing | 2021-03-23 | 2021-03-23
14 | Sprint 2 | Project 2 | Task 12 | 2 | 3 | Resource 1 | In Progress | Testing | 2021-03-23 | 2021-03-23
15 | Sprint 3 | Project 1 | Task 10 | 2 | 2 | Resource 1 | Done | Testing | 2021-03-24 | 2021-03-24
16 | Sprint 3 | Project 1 | Task 11 | 1 | 1 | Resource 1 | Done | Testing | 2021-03-24 | 2021-03-24
17 | Sprint 3 | Project 1 | Task 12 | 1 | 1 | Resource 1 | Done | Development | 2021-03-24 | 2021-03-24
18 | Sprint 3 | Project 1 | Task 13 | 1 | 1 | Resource 2 | Done | Testing | 2021-03-24 | 2021-03-24
19 | Sprint 3 | Project 1 | Task 14 | 2 | 2 | Resource 2 | Done | Development | 2021-03-24 | 2021-03-24
20 | Sprint 4 | Project 3 | Task 15 | 3 | 3 | Resource 1 | Done | Development | 2021-03-25 | 2021-03-25
21 | Sprint 4 | Project 3 | Task 16 | 1 | 1 | Resource 2 | Done | Development | 2021-03-25 | 2021-03-25
22 | Sprint 4 | Project 3 | Task 17 | 2 | 2 | Resource 2 | Done | Development | 2021-03-25 | 2021-03-25
23 | Sprint 4 | Project 3 | Task 18 | 1 | 1 | Resource 1 | Done | Testing | 2021-03-25 | 2021-03-25
24 | Sprint 4 | Project 3 | Task 19 | 1 | 1 | Resource 2 | Done | Testing | 2021-03-25 | 2021-03-25
25 | Sprint 4 | Project 3 | Task 20 | 1 | 1 | Resource 1 | In Progress | Testing | 2021-03-25 | 2021-03-25
26 | Sprint 4 | Project 3 | Task 21 | 2 | 2 | Resource 2 | In Progress | Testing | 2021-03-25 | 2021-03-25